## (THCM) E
[17 empty] | Complete |  |  | Third year |  |  | Second year |  |  | First year |  |  | Create
| Environment Promotion Department | [15 empty] | Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date
| Manager | Responsible person | Personnel | Environmental audit pointed out, request matters answer form | [12 empty] | Manager | Responsible person | Personnel | Manager | Responsible person | Personnel | Manager | Responsible person | Personnel | Manager | Responsible person | Personnel | Manager | Responsible person | Personnel
*Evaluation
| NC（Non-Compliance） | [14 empty] | Name of Company : Tata Hitachi Construction Machinery
| PC（Potential Non-Compliance） | [14 empty] | Date : 19/04/2021
| BMP（Best Management Practice） |  | Status of previous audit open points
№ | Matters that need improvement by audit |  |  |  | *Evaluation as on Jan'2021 | Improvement measures | Completion date(for corrected issues) | Expected completion date (correction under progress) | goal | Department in charge | Schedule |  |  |  |  | Remarks | Improvement situation End of April. 2021 |  |  | Progress status | Improvement situation End of Sep. 2021 |  |  | Progress status |  |  |  | Progress status |  |  |  | Progress status | Completion date | Evidence
[11 empty] | Second half of 2020 | First half of 2021 | Second half of 2021 | First half of 2022 | Second half of 2022
1 | The Site is reported to be recycling treated wastewater (process and sanitary) for reusing in process and gardening purposes respectively for maintaining zero discharge conditions. However interviews with Site EHS personnel it has been revealed that no formalized and documented water balance details are available at the Site for objective demonstration of facts and figures related to groundwater abstraction, use, recycle/reuse towards fulfilment of complete zero discharge conditions. |  |  |  | open | Water balance diagram prepared (in line with recommendations by Audit team). | 01.02.2021 | [25 empty] | 01.02.2021
2 | The Site is reported to be sourcing the present water requirements through two (2) borewells operating at the acility. Based on the review of October 2018 groundwater abstraction records, it has been revealed that the Site is actually abstracting total 492 kilo litres (KL) of groundwater per day basis, which is approximately 1,038% more than the permitted total water consumption quantity as specified under the Consent to Operate issued by WBPCB. |  |  |  | open | Plan for water conservation is under implementation e.g. commissioning of new fire hydrant line to reduce losses due to under ground leakage |  | 15.02,2022 | [7 empty] | 1> Monthly report shall be monitored | [16 empty] | 15.02,2022
3 | The Site is reported to generate nominal quantities (approximately less than 50 grams per day) of bio-medical waste from first-aid treatments undertaken at the on-site OHC. 1. ERM has noted that the Site does not maintain the regulatory requirement regarding submission of annual report with respect to the bio-medical waste generated to the West Bengal Pollution Control Board (WBPCB). 2. Furthermore, the Site representatives were unaware of the regulatory requirement to upload the Annual Return to the company’s web site. |  |  |  | open | 1> Form IV (annual report ) submitted for 2020 2> The same will be uploaded at THCM web site | 1> 12.02.2021 | 2> 15.06.2021 | [24 empty] | 1> 12.02.2021 2> 15.06.2021
4 | Interviews with the Site EHS personnel has revealed that, the Site is not aware on the respective regulatory requirements and yet to designate a systematic approach to review and monitor the activities related to bio- medical waste management on periodic basis as required under Bio-Medical Waste Management Rules, 2016. |  |  |  | partially close | Monthly review will be made by Head - EHS from April'2021 |  | 15.06.2021 | [24 empty] | 15.06.2021
5 | As reported by the Site EHS personnel, all electronic wastes (e-wastes) generated at the Site are transferred to THCM Bangaluru office in India, which in turn centrally dispose all e-wastes generated by pan India THCM facilities through an authorized recycling agency named M/s. Pruthvi E-Recycle Pvt. Ltd., Rajkot. All requisite regulatory documentation related to e-wastes disposal are being maintained centrally at the THCM Bangaluru office. However, interviews revealed that the Site personnel was neither aware of the requirement to maintain records of e-waste generated by them in Form-2, or submit Form 3 to the WBPCB towards annual returns under the E-Waste (Management) Rules, 2016, nor the Site maintains of any such documented records against regulatory requirements for scrutiny by the concerned State Pollution Control Board (WBPCB in this case). |  |  |  | partially close | Form 2 & 3 are to be submitted to WBPCB from 2021 |  | 30.06.2021 | [24 empty] | 30.06.2021
6 | The Site is reported to be transferring the e-wastes generated through its Bangaluru office in India, which in turn centrally disposes all e-wastes generated by pan India THCM facilities through an authorized recycler agency named M/s. Pruthvi E-Recycle Pvt. Ltd., Rajkot. However, interviews revealed that the Site does not have the clarity and documented traceability regarding the valid authorization status of the designated external agency M/s. Pruthvi E-Recycle Pvt. Ltd., Rajkot being used as the third party e-wastes recycler. |  |  |  | partially close | Authorisation document attached | 01.02.2021 | [8 empty] | Authorisation doc. Recd. | [16 empty] | 01.02.2021
7 | During Site walkthrough at the designated Hazardous Waste Shed, it has been noted that approximately 23 mild steel barrels containing used oil were stored (each barrel with tentative storage capacity of 200 liters). This translates to approximately 4,600 liters of used oil stored at the time of the Site audit. The used oil barrel storage section under the designated Hazardous Waste Shed was found with oil spill marks on the concrete floor along with spilled oily sludge observed beneath the plastic pellets used for the storage of used oil barrels. The Hazardous Waste Shed was noted to be not provided with any emergency preparedness arrangements in terms of Spill Containment and Secondary Containment systems in the event of loss of integrity or container failure and to prevent any further contamination risk to the environment and human health. [Definition: Secondary containment is defined as a means of surrounding one or more primary storage containers to collect any hazardous material spillage in the event of loss of integrity or container failure.] |  |  |  | partially close | Secondary containment of 220 L tr installed in April'2021 | 12.04.2021 | [25 empty] | 12.04.2021
Status of new audit points
1 | Integration of Jamshedpur plant with the Kharagpur plant has been completed during early 2020. Due to this ntegration, production of Heavy Excavators (8 nos per month) and Gear Box Assembly (400 nos per month) added to the Kharagpur plant. New facilities were also added which include transmission shop, material shop, heavy excavator fabrication and assembly. This expansion activities has contributed increased consumption of raw materials and relevant resources in absolute terms. It has been noted that the Site has submitted application towards amended Consent To Establish (CTE) issuance from West Bengal Pollution Control Board (WBPCB) along with requisite fees during end of 2019. Reportedly Site EHS team has subsequently followed up with WBPCB on verbal basis only without any documentary trail. However, issuance of the revised CTE (NOC)1 from WBPCB was still awaited as on the date of Site audit. |  |  |  | NC | NOC from WBPCB received | 23.03.2021 | [25 empty] | 23.03.2021
2 | In continuation with the previous Consent to Operate (CTO) which was valid till 31 December 2018, reportedly the Site has applied for renewal of the CTO from WBPCB and has received renewed CTO under Section 25 & 26 of the Water (Prevention and Control of Pollution) Act, 1974 and Section 21 of the Air (Prevention and Control of Pollution) Act, 1981 only on 17.12.2020 (Consent letter no. C0109293 Dated: 17.12.2020; valid upto 31.12.2023). Firstly, with reference to the above stated CTO renewal timeline it has been observed that the Site has operated almost two years (January, 2019 – Decemeber, 2020) without a valid CTO from WBPCB. Secondly, the review of the renewed CTO dated 17.12.2020 has revealed that none of the permitted/stipulated conditions as mentioned under the currently valid CTO reflects the present site operational details production capacity, raw material usage, resource consumption, waste generation etc. including Site expansion components. |  |  |  | NC | CTO for augmented capacity shall be obtained after expiry of the present consent in 2023 |  | 31.12.2023 | [24 empty] | 31.12.2023
3 | Based on the Site observations and interviews conducted with the Site team during the audit process has revealed that, the Site is not aware requirement of greenbelt development on at least 33% of the land area as per the conditions stipulated under regulatory permits CTE dated 13.07.2009 and CTO dated 17.12.2020 specifying the Site shall develop 33% of the available open land under greenbelt coverage. The Site is yet to map and clearly estimate about the total designated greenbelt area existing within the facility. As per the below land coverage details produced during site audit, total vacant area includes demarcated future expansion plots, open grassy patches, landscaped areas and areas with plantation.Moreover, based on the site visit observations the areas covered by tree plantation (excluding landscaped and grassy patch areas) were found apparently less against the stipulated 33% land area greenbelt development requirement. |  |  |  | NC | Green belt development plan made | 12.04.2021 | [25 empty] | 12.04.2021
4 | The Site has obtained regulatory approval for sinking new two (2) borewells from the West Bengal State Level Ground Water Resources Development Authority (State Water Investigation Directorate) vide Permit dated 12th December 2018. The Permit has granted groundwater abstraction capacity for both borewells with 30m3/hour for 8 hours per day capacity. Reportedly Site is alternatively operating these two (2) borewells to meet the water demand at the plant. However, on ample basis based on the review of November and December 2020 groundwater abstraction dataset, it has been revealed that the Borewell-2 has been used more often than the Borewell-1. No data regarding the abstraction rate and operation hours were available for both the borewells. The total withdrawal from Borewell- 2 was found to be exceeding the combined permitted quantity of 240m3/day for most of the time during November and December 2020 as reviewed demonstrating an imbalance in utilizing both the borewells. This borewell operational approach was found to be in contradiction with the stipulated permit condition. |  |  |  | NC | A new borewell shall be installed to maintain the hourly abstraction rate |  | 15.02,2022 | [24 empty] | 15.02,2022
5 | During Site walk at the backyard of the Frame Paint Shop, it has been observed that around 20 to 25 numbers empty paint containers of different sizes were temporarily stored within a large metal container. However, no overheaad cover along with access restrictions were provided around that temporary storage place (Refer Picture 7). As per the Hazardous and Other Wastes (Management and Transboundary Movement) Rules, 2016, Schedule 1, Category 33.1 empty paint containers are categorized as regulated hazardous waste. Such open storage practices of the hazardous wastes was found to be noncomplying with the specific condition mentioned under Hazardous Waste Authorization dated 06.06.2019. Moreover, such storage practices during rainy season increases risk of unwanted contamination to the environment and human health. |  |  |  | NC | New shed for empty paint drum storage shall be made (PDC- May'2021) |  | 30.06.2021 | [24 empty] | 30.06.2021
6 | As part of the integrtion of Jamshedpur plant with the Kharagpur plant, i.e onsite expansion project, the Site has introduced onsite storage and use of Ammonia (48 numbers of cylineders X 40 kg), Liquide Oxygen (6064 kg) and Methanol (12.6 KL). The Site has also constructed a new underground storage tank (2X20 KL) for diesel (Refer Picture 5). All the above four (4) chemical categories qualifies as hazardous chemicals as per Schedule 1 Part-I&II of anufacture, Storage and Import of Hazardous Chemical Rules, 1989, and Amendment Rules in 2000. Based on the interview of site personnel and review of the documentary evidence, the site has a documented On-site Emergency Plan in place including defined hazard identification and disaster plan approach. Site is also conducting periodic mock-drills. However, the onsite emergency response plan reviewed for the Site was found to be prepared on 01.04.2018 and subsequently not reviewed to check sufficiency of the existing plan and revised on account of Site expansion completed during early 2020 from both regulatory requirement and risk management perspectives. |  |  |  | PC | Revision of on site emrgency plan is under progress |  | 30.06.2021 | [24 empty] | 30.06.2021
7 | During Site inspection at the designated Paint Store, it was observed that different sizes (ranging from 500ml to max. 20L) of paint containers comprisiong of two types namely primer and top-coat along with containers of thinner (20L) were stored. At the time of audit, there were approximately 100 numbers X 5L paint containers, 110 numbers X 10L paint containers, 70 numbers X 20L paint containers and 26 numbers X 20L thinner container stored at the Paint Store Room (refer Picture 9). Reportedly, the loading and unloading of the paint and thinner containers are done manually. At the designated Paint Store room, there were no secondary containment arrangement found. Furthermore, there were high volume containers i.e. 20L containers were found stored in the rack at a height of more than 4.5 ft from the floor level. Further the entry slope/ramp of the Paint Store were found to be steep (>30°) and the bund was broken (refer Picture 11). Two of the thinner containers stored at height (more than 4.5 ft. from floor level) were observed cranked (refer Picture 10). Due to the storage pattern (involving accidental fall and container breach risk, absence of secondary containment, steep loading and unloading base slope) and risk based approach, this may lead to accidental spill and unwanted contamination to the environment (soil). |  |  |  | BMP | 1> Heavy containers stored at bottom most level 2> Pit made for secondary containment | 05.03.2021 | [25 empty] | 05.03.2021
8 | Review of the on-site Emergency Response Plan (ERP) available at the Site has revealed that, fire emergency has been considered as one of the major emergency situation and laid out ERP accordingly. However, the ERP has not considered an outline the management procedure related to wastewater generated due to any fire event. In the event of any fire accident, large volume of wastewater containing pollutants will be generated depending on the severity of the fire. Interviews with the Site Team revealed that the wastewater which will be generated during fire event will be diverted through the storm water drainage network. The storm water drainage network are connected to the peripheral drainage system of the Site which is thereafter connected to the discharge drain located outside the plant boundary. At the discharge point, there is no effluent control system (such as oil and grease separator etc.) arrangement is available to control any such accidental wastewater discharge event. |  |  |  | BMP | Proposal under review |  | 15.07.2022 | [7 empty] | Proposal under review | [16 empty] | 15.07.2022

## Sheet1
Complete |  |  | Third year |  |  | Second year |  |  | First year |  |  | Create
Date |  |  | Date |  |  | Date |  |  | Date |  |  | Date
Manager | Responsible person | Personnel | Manager | Responsible person | Personnel | Manager | Responsible person | Personnel | Manager | Responsible person | Personnel | Manager | Responsible person | Personnel